## Issues
RIZAP CRM Issues
no. | Report Date | Reporter | Problem description | Analysis | Solution
1 Closed | 2021-06-17 | Benjamin | [Bug type: CSV export] 黃思恬 Admission Fee recognize date incorrect | [2021-06-24 Paul Kang:] The export used the created date instead of the actual first session date. Fixed buy using actual first session date. | [2021-06-24 Paul Kang:] Closed Fixed in v1.6 version. Confirmed by Benjamin at 7/1
2 | 2021-06-21 | Benjamin | [Bug type: CSV export] 中川佐知子 Year Contract "Refund sessions" and "Refund amount" | [2021-06-24 Paul Kang:] Need to clear definitions of Year Contract "Refund sessions" and "Refund amoung". | [2021-07-12 Paul Kang:] 2012-07-12 Benjamin confirmed the definitation of "Refund amount". Benjamin replied the definitioons on 7/22. Under discussion, please see E15 in the YearContract worksheet
3 | 2021-07-13 | Fiona | [Bug type: Expiration Date] With Contract CTTW000393, the first session date was 2021/05/07, so the expiration date should be 2021/08/07, but the expiration date in database was incorrect 2021/06/21. So the contract was completed at 6/21. | [2021-07-15 Paul Kang]: Everyday at 23:00, a scanning program running in Microsoft server will scan the sessions that day. If first sessions are found, the program will update the expiration date of the contracts. It seems Microsoft server was crash at the evening of 6/21. The scanning program failed to run, so the contract expiration date was not updated. | [2021-07-15 Paul Kang] Closed The scanning program need to scan not only that day, but scan moreday before. Use a flag to identify the update the expiration date. This is done at 2021-07-19. UI display: Discussed in 2021-07-29 MTG. Closed Because the expiration date is updated by the scanning program at night. The CRM UI display of the expiration date will not be correct if we show the expiration date in the database. So the UI now display "First Session date + course period" which may not be consistent with the expiration date.
4 | 2021-07-14 | Fiona | [Bug type: Expiration Date] With Contract CTTW000421, the first session date was 2021/04/16, so the expiration date should be 2021/07/16, but the expiration date in database was incorrectly 2021/07/12. So the contract was completed at 7/12. | [2021-07-15 Paul Kang]: From the database, the first session at 4/16 was enterred in 4/18 manually. So the scanning program ran at 4/16 didn't update the expiration date. At 4/18, even the first session of 4/16 was enterred by hand, the scanning program did not scan 4/16 sessions again, so the expiration date was not updated either.
5 | 2021-07-15 | Benjamin | [Type: CSV column data defination] For management purpose, Benjamin requests the CSV sessions data follow RIZAP control excel format. | [2021-07-15 Paul Kang]: Please Benjamin to provide the screenshots of 中川 sessions and 三宅 rizap control excel for reference. uCare will evaluate the effoerts/time. [2021-07-16]: Benjamin provides the powerpoint and csv files. [2017-07-21 Paul Kang]: 1. Sales management is dffferent from the Sessions CSV files. We found a bug of deducting the products amount again. 2. RIZAP would like the Sessions CSV data needs to reflect the session status according to date. No historical statistic of each session in database. It would need to trace back to re-calculate the historical data. | [2021-07-28 Paul Kang]: 1. The bug of deducting the products amount is fixed on 7/28. 2. Sessions CSV data needs to reflect the session status according to date. This would would be fixed by 8/4. 3. Instead of CSV export file, uCare implements Sessions data in the Web tools. https://rizap-crm.github.io/web-tools/indexV2Alpha.html
6 | 2021-07-15 | Paul Kang | [Type: Information] 1. If the fiscal year of RIZAP USA also starts from 1st of April? 2. In current CRM, guest check-in uses LINE and staff check-in uses fingerprint. Please RIZAP double check if USA can use the same check-in mechod. 3. Due to different currencies, CRM use numbers like NT$1234. With US$, maybe need to change to US$12.34? [2021-07-27] 4. ContarctID and GuestId like CTWxxxxx and TWyyyyy changed to something like CUSxxxxx and USyyyyy? | [2021-07-21 Kobayashi]: 1. The fiscal year of RIZAP USA ->Yes, Start from 1st of April 2. Check-in method -> Not same in Taiwan, Don't use these tools(Line, Finger print) to avoid any error in US. The key-in by manual is ok. 3. Currency -> Yes, your understanding is correct.
7 Closed | 2021-07-17 | Fiona | After cancel the contract of 夏道緣, cannot create new contract for 夏道緣。 | [2021-07-18 Paul Kang]: The contract cancelled was the only one contract of 夏道緣, deleting it will cause conflicts in the database. | [2017-07-18 Paul Kang]: Closed It needs to delete 夏道緣 from the Guest Management, then create a new guest for 夏道緣 with a contract from the Cuest Inquery.
8 Closed | 2021-07-22 | Fiona | Can not login with hg@gmail.com account/password | [2021-07-23 Paul Kang]: The password of hq@gmail.com was reset three times by clicking "Forget Your Password?" in te morning of 7/22. The reset emails were send to a void email address, hq@gmail.com. | [2021-07-23 Paul Kang]: Closed Solution: Recover the password from thr backup database. Suggestion: Create a new HQ account and use the working email address.
10 | 2021-08-04 | Yuma | [Type: CSV YearContract Data incorrect] The records in column M are in the correct state if they are above 0, but there are some that are -1. Please investigate the cause. | [2021-08-04 Paul Kang]: Under investigation

## Close Issues
RIZAP CRM Issues
no. | Report Date | Reporter | Problem description | Analysis | Solution
1 Closed | 2021-06-17 | Benjamin | [Bug type: CSV export] 黃思恬 Admission Fee recognize date incorrect | [2021-06-24 Paul Kang:] The export used the created date instead of the actual first session date. Fixed buy using actual first session date. | [2021-06-24 Paul Kang:] Closed Fixed in v1.6 version. Confirmed by Benjamin at 7/1
3 Closed | 2021-07-13 | Fiona | [Bug type: Expiration Date] With Contract CTTW000393, the first session date was 2021/05/07, so the expiration date should be 2021/08/07, but the expiration date in database was incorrect 2021/06/21. So the contract was completed at 6/21. | [2021-07-15 Paul Kang]: Everyday at 23:00, a scanning program running in Microsoft server will scan the sessions that day. If first sessions are found, the program will update the expiration date of the contracts. It seems Microsoft server was crash at the evening of 6/21. The scanning program failed to run, so the contract expiration date was not updated. | [2021-07-15 Paul Kang] Closed The scanning program need to scan not only that day, but scan moreday before. Use a flag to identify the update the expiration date. This is done at 2021-07-19. UI display: Discussed in 2021-07-29 MTG. Closed Because the expiration date is updated by the scanning program at night. The CRM UI display of the expiration date will not be correct if we show the expiration date in the database. So the UI now display "First Session date + course period" which may not be consistent with the expiration date.
4 Closed | 2021-07-14 | Fiona | [Bug type: Expiration Date] With Contract CTTW000421, the first session date was 2021/04/16, so the expiration date should be 2021/07/16, but the expiration date in database was incorrectly 2021/07/12. So the contract was completed at 7/12. | [2021-07-15 Paul Kang]: From the database, the first session at 4/16 was enterred in 4/18 manually. So the scanning program ran at 4/16 didn't update the expiration date. At 4/18, even the first session of 4/16 was enterred by hand, the scanning program did not scan 4/16 sessions again, so the expiration date was not updated either.
7 Closed | 2021-07-17 | Fiona | After cancel the contract of 夏道緣, cannot create new contract for 夏道緣。 | [2021-07-18 Paul Kang]: The contract cancelled was the only one contract of 夏道緣, deleting it will cause conflicts in the database. | [2017-07-18 Paul Kang]: Closed It needs to delete 夏道緣 from the Guest Management, then create a new guest for 夏道緣 with a contract from the Cuest Inquery.
8 Closed | 2021-07-22 | Fiona | Can not login with hg@gmail.com account/password | [2021-07-23 Paul Kang]: The password of hq@gmail.com was reset three times by clicking "Forget Your Password?" in te morning of 7/22. The reset emails were send to a void email address, hq@gmail.com. | [2021-07-23 Paul Kang]: Closed Solution: Recover the password from thr backup database. Suggestion: Create a new HQ account and use the working email address.

## Session
Session Column | Definition (2021-07-28 By Paul Kang and Benjamin
日期 | 上課日期
店鋪 | 上課店鋪
客戶名稱 | 客戶名字
客戶編號 | 客戶編號
合約編號 | 合約編號
負責教練 | 負責教練
合約名稱 | 合約名稱
合約時間(月) | 該課程預定的執行月份
合約簽訂日期 | 合約上的簽訂日期
合約開始日期 | 第一堂上課的日期
合約期限 | 合約到期日期
合約已進行(月) | (此 session 日期 - 合約簽訂日期)/30 天
合約總價(含稅) | 合約總價(含稅)
合約總價(未稅) | 合約總價(未稅)
合約狀態 | 合約狀態
開始後來店頻率 | (此 session 的合約已執行堂數)/合約已進行(月)
堂數排序 | 此 session 在該店當天的第幾堂課
合約堂數 | 合約堂數
合約已執行堂數 | 合約在此 session 的已執行堂數
合約退會堂數 | ??? see YearContract Row#15
合約剩餘堂數 | 合約堂數 - 合約已執行堂數
課程單價(未稅) | 合約總價(未稅)/合約堂數
合約已認列金額(已稅) | 此 session 的合約已執行堂數 * 課程單價(已稅)
合約已認列金額(未稅) | 此 session 的合約已執行堂數 * 課程單價(未稅)
合約未認列金額(已稅) | 合約總價(含稅) - 合約已認列金額
合約未認列金額(未稅) | 合約總價(未稅) - 合約已認列金額(未稅)
當日認列金額(未稅) | 上課該店當天到此 session 的累積認列金額(未稅)

## AdmissionFee
Admission Fee Column | Definition (2021-07-28 By Paul Kang and Benjamin
首次課程日期 | 合約第一次上課時間
店鋪 | 上課店鋪
客戶名稱 | 客戶名字
客戶編號 | 客戶編號
合約編號 | 合約編號
負責教練 ==> 簽約員工 | 2021-08-02 Paul 和 Benjamin 討論改為 簽約員工
合約名稱 | 合約名稱
合約時間(月份) | 該課程預定的執行月份
合約簽訂日期 | 合約上的簽訂日期
已認列入會費 | 已認列入會費
已認列入會費(未稅) | 已認列入會費(未稅)
發票種類 | 發票種類
發票發行日期 | 發票發行日期
發票號碼 | 發票號碼

## Product
Product Column | Definition (2021-07-28 By Paul Kang and Benjamin
購買日期 | 購買日期
店鋪 | 購買商品的店鋪
客戶名稱 | 客戶名字
客戶編號 | 客戶編號
合約編號 | 合約編號
負責教練 | 負責教練
產品名稱 | 產品名稱
產品單價 | 產品單價
產品單價(未稅) | 產品單價(未稅)
產品數量 | 產品數量
合約總價(含稅) | 合約總價(含稅)
合約原價(未稅) | 合約原價(未稅)
付款日 | 付款日
金額 | 金額
付款方式 | 付款方式
發票種類 | 發票種類
發票發行日期 | 發票發行日期
發票號碼 | 發票號碼

## YearContract
| Product Column | Definition (2021-07-28 By Paul Kang and Benjamin
A | 店鋪 | 上課店鋪
B | 客戶名稱 | 客戶名字
C | 客戶編號 | 客戶編號
D | 合約編號 | 合約編號
E | 負責教練 | 負責教練
F | 合約名稱 | 合約名稱
G | 合約簽訂日期 | 合約上的簽訂日期
H | 合約總價(含稅) | 合約總價(含稅)
I | 合約原價(未稅) | 合約總價(未稅)
J | 合約狀態 | 合約狀態
K | 合約堂數 | 合約堂數
L | 已使用堂數 | 合約已執行堂數
M | 剩餘堂數 | 剩餘堂數
N | 退費堂數 | 定義??????? | 2021-7-22 Benjamin: Case1: 假設10堂，共10萬元 3/31前付清，並執行了6次 於4/01全額退費 表示方式如下 Q列 前年度剩餘堂數 4 R列 3/31之前已認列金額 6萬 S列 3/31之前合約剩餘金額(未稅) 38,095.23元 AY列 折讓金額 10萬元 事務所指示，如能將折讓金額分為兩種會更好理解。 勞務收入折讓 6萬元 預收折讓 4萬元 >>> 前年度剩餘4萬 折讓10萬、10堂 ? 取消0萬、0堂 ? | Simulated case, please Benjamin confirm Case2: 假設10堂，共10萬元 3/31前付 8 萬元，並執行了6次 於4/01全額退費 表示方式如下 Q列 前年度剩餘堂數 4 R列 3/31之前已認列金額 6萬 S列 3/31之前合約剩餘金額(未稅) 38,095.23元 AY列 折讓金額 8萬元 Ben: 2021-08-02 關於上回的問題， 假設10次10萬，上年度付了8萬，上了6堂，本年度退費 >>> 前年度剩餘4萬 折讓2萬、2堂, 跟 AY列 折讓金額 8萬元不同? 取消2萬、2堂 | Simulated case, please Benjamin confirm Case3: 假設10堂，共10萬元 4/1 開始，7/1 前付 8 萬元，並執行了6次 於7/2 全額退費 表示方式如下 Q列 前年度剩餘堂數 0 R列 3/31之前已認列金額 0 S列 3/31之前合約剩餘金額(未稅) 0元 AY列 折讓金額 8萬元 問題: T~V 和 AG~AI 仍需記錄嗎?
O | 課程單價(含稅) | 合約總價(含稅)/合約堂數
P | 課程單價(未稅) | 合約總價(未稅)/合約堂數
Q | 前年度剩餘堂數 | 前年度剩餘堂數
R | 3/31之前已認列金額 | 3/31之前已認列金額
S | 3/31之前合約剩餘金額(未稅) | 3/31之前合約剩餘金額(未稅)
T | 2021/4已使用 | 此合約於 2021 年 4 月使用的堂數
U | 2021/5已使用 | 此合約於 2021 年 5 月使用的堂數
V | 2021/6已使用 | 此合約於 2021 年 6 月使用的堂數
W | 2021/7已使用 | 此合約於 2021 年 7 月使用的堂數
X | 2021/8已使用 | 此合約於 2021 年 8 月使用的堂數
Y | 2021/9已使用 | 此合約於 2021 年 9 月使用的堂數
Z | 2021/10已使用 | 此合約於 2021 年 10 月使用的堂數
AA | 2021/11已使用 | 此合約於 2021 年 11 月使用的堂數
AB | 2021/12已使用 | 此合約於 2021 年 12 月使用的堂數
AC | 2022/1已使用 | 此合約於 2022 年 1 月使用的堂數
AD | 2022/2已使用 | 此合約於 2022 年 2 月使用的堂數
AE | 2022/3已使用 | 此合約於 2022 年 3 月使用的堂數
AF | 前年度未認列(未稅) | ?????
AG | 2021/4已認列 | 此合約於 2021 年 4 月認列的金額(未稅)
AH | 2021/5已認列 | 此合約於 2021 年 5 月認列的金額(未稅)
AI | 2021/6已認列 | 此合約於 2021 年 6 月認列的金額(未稅)
AJ | 2021/7已認列 | 此合約於 2021 年 7 月認列的金額(未稅)
AK | 2021/8已認列 | 此合約於 2021 年 8 月認列的金額(未稅)
AL | 2021/9已認列 | 此合約於 2021 年 9 月認列的金額(未稅)
AM | 2021/10已認列 | 此合約於 2021 年 10 月認列的金額(未稅)
AN | 2021/11已認列 | 此合約於 2021 年 11 月認列的金額(未稅)
AO | 2021/12已認列 | 此合約於 2021 年 12 月認列的金額(未稅)
AP | 2022/1已認列 | 此合約於 2022 年 1 月認列的金額(未稅)
AQ | 2022/2已認列 | 此合約於 2022 年 2 月認列的金額(未稅)
AR | 2022/3已認列 | 此合約於 2022 年 3 月認列的金額(未稅)
AS | 合約已認列收入 | 合約已認列收入(含稅)
AT | 合約已認列收入(未稅) | 合約已認列收入(未稅)
AU | 合約未認列金額 | 合約未認列金額(含稅)
AV | 合約未認列金額(未稅) | 合約未認列金額(未稅)
AW | 顧客已付(含稅) | 退費後還要記錄?
AX | 未付款 | 合約金額減除已付款
AY | 折讓金額 |  | 請考慮入會費和手續費的例子
AZ | 退費金額
BA | 付款日1 | 付款日1
BB | 付款方式 | 付款方式
BC | 金額 | 金額
BD | 發票種類 | 發票種類
BE | 發票發行日期 | 發票發行日期
BF | 發票號碼 | 發票號碼
BG | 付款日2 | 付款日2
BH | 付款方式 | 付款方式
BI | 金額 | 金額
BJ | 發票種類 | 發票種類
BK | 發票發行日期 | 發票發行日期
BL | 發票號碼 | 發票號碼